## AAB start
Name:
Student number:
Please select the approximate unit price for the product you have chosen:
(select)
unit price < R100
R100 ≤ unitprice < R1000
unit price ≥ R1000
1.1364
1. Use this data for a)-d):
Annual demand (D) = |  | 100 |  |  |  | R100 ≤ unitprice < R1000 | 1a) |  | 20
Work days per year = |  | 88
Ordering cost (Co) = |  | 8 |  |  |  |  | 1b) |  | 5
Carying cost (Ch) = |  | 2 | % of the unit price |  | 4
Unit price (P) = |  | 200 |  |  |  |  | 1c) |  | 6.8182 | ≈ 7
Lead time (L) = |  | 6 | [10 empty] | order+holding
e) Setup cost (Cs) = |  | 20 |  |  |  |  | 1d) |  | 20.4545 | ≈ 21 |  |  | 80
Daily production rate (p) = |  | 2 | [10 empty] | setup | holding
f) Number of units ordered = |  | 22 | [7 empty] | 48.1227 |  |  | 41.5605 | 41.5605 | 83.1209
1e)
2. Activity |  |  | Duration (weeks) | Predecessor(s) | Activity cost (Rands) |  | 1f) |  |  |  | 36.3636
A. Write instructions |  |  | 4 | - | 1000
B. Select operators |  |  | 4 | - | 2000
C. Train operators |  |  | 2 | A, B | 4000
D. Announce new service |  |  | 3 | B | 3000
E. Purchase, ship, and receive equipment |  |  | 9 | - | 13000
F. Test new operators on equipment |  |  | 4 | C, E | 5000
|  |  |  | A | 4
|  |  |  | 0 | 4 |  |  | C | 2
|  |  |  | 3 | 7 |  |  | 4 | 6
|  | Start | [5 empty] | 7 | 9 |  | F | 4 |  | End
|  |  |  | B | 4 | [5 empty] | 9 | 13
|  |  |  | 0 | 4 |  |  | D | 3 |  | 9 | 13 |  | EF
|  |  |  | 3 | 7 |  |  | 4 | 7
[8 empty] | 10 | 13
|  |  |  | E | 9
|  |  |  | 0 | 9
|  |  |  | 0 | 9
1. This question relates to one of the products that your company provides. Select the approximate price range for this product above and generate your data. The annual demand (D) is constant throughout the year. Use the information provided for each part of the question.
2. You decide to prepare for the manufacturing process while your analysis is being done. You identify the following steps for this process:
(1) write instructions and procedures,
(2) select techniques to operate the equipment, and
(3) procure the equipment.
The instructions and selection of the operators has to be completed before the training could commence. It is also necessary to choose the operators and evaluate their qualifications before formally announcing the new service to the local community. Upon arrival and installation of the equipment and completion of the operators' training, you will have to spend a period checking out the procedures, operators, and equipment before declaring that the project was successfully completed. Find your data in cells A33 through G39.

## Project crashing
Activity | Normal Time | Crash Time | Normal Cost | Total Cost with Crashing
A | 4 | 3 | 1000 | 2000
B | 4 | 4 | 2000 | 2000
C | 2 | 1 | 4000 | 5000
D | 3 | 3 | 3000 | 3000
E | 9 | 7 | 13000 | 17000
F | 4 | 4 | 5000 | 5000